## Test Scenarios
Scenario ID | Module | Test Scenario | High
TS-001 | Login | Verify login with valid credentials | High
TS-002 | Login | Verify login with invalid username | High
TS-003 | Login | Verify login with invalid password | High
TS-004 | Login | Verify login with empty username and password | High
TS-005 | Login | Verify logout functionality | Medium
TS-006 | Products | Verify products are displayed correctly | High
TS-007 | Products | Verify product name is displayed correctly | Medium
TS-008 | Products | Verify product price is displayed correctly | Medium
TS-009 | Products | Verify product image is displayed correctly | Low
TS-010 | Products | Verify product description is displayed correctly | Low
TS-011 | Sorting | Verify sorting by Name A to Z | Medium
TS-012 | Sorting | Verify sorting by Name Z to A | Medium
TS-013 | Sorting | Verify sorting by Price low to high | Medium
TS-014 | Sorting | Verify sorting by Price high to low | Medium
TS-015 | Cart | Verify user can add a product to cart | High
TS-016 | Cart | Verify selected product appears in cart | High
TS-017 | Cart | Verify user can remove product from cart | High
TS-018 | Cart | Verify cart displays correct product price | Medium
TS-019 | Cart | Verify cart quantity is displayed correctly | Medium
TS-020 | Cart | Verify Continue Shopping functionality | Medium
TS-021 | Checkout | Verify user can open checkout | High
TS-022 | Checkout | Verify checkout form fields | High
TS-023 | Checkout | Verify checkout with valid information | High
TS-024 | Checkout | Verify checkout with empty required fields | High
TS-025 | Checkout | Verify user can complete an order | High
TS-026 | Checkout | Verify order confirmation message | High
TS-027 | Menu | Verify menu can be opened | Low
TS-028 | Menu | Verify All Items option | Medium
TS-029 | Menu | Verify About option | Low
TS-030 | Menu | Verify Reset App State functionality | Medium

## Test Cases
Test Case ID | Scenario ID | Module | Test Case | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-001 | TS-001 | Login | Verify user can login with valid credentials. | User is on the SauceDemo login page. | 1. Enter valid username. 2. Enter valid password. 3. Click the Login button. | Username: standard_user Password: secret_sauce | User should be successfully logged in and redirected to the Products page. | User was successfully logged in and redirected to the Products page. | PASS | High
TC-002 | TS-002 | Login | Verify login with invalid username | User is on the SauceDemo login page. |  |  |  | Error message "Epic sadface: Username and password do not match any user in this service" was displayed and the user was not logged in. | PASS
TC-003 | TS-003 | Login | Verify login with invalid password | User is on the SauceDemo login page. |  |  |  | Error message "Epic sadface: Username and password do not match any user in this service" was displayed and the user was not logged in. | PASS
TC-004 | TS-004 | Login | Verify login with empty username and password | User is on the SauceDemo login page. |  |  |  | Error message "Epic sadface: Username is required" was displayed and the user was not logged in. | PASS
TC-005 | TS-005 | Login | Verify logout functionality | User is successfully logged in and is on the Products page.
TC-006 | TS-006 | Products | Verify products are displayed correctly | User is successfully logged in and is on the Products page.
TC-007 | TS-007 | Products | Verify product name is displayed correctly | User is successfully logged in and is on the Products page.
TC-008 | TS-008 | Products | Verify product price is displayed correctly | User is successfully logged in and is on the Products page.
TC-009 | TS-009 | Products | Verify product image is displayed correctly | User is successfully logged in and is on the Products page.
TC-010 | TS-010 | Products | Verify product description is displayed correctly | User is successfully logged in and is on the Products page.
TC-011 | TS-011 | Sorting | Verify sorting by Name A to Z | User is successfully logged in and is on the Products page.
TC-012 | TS-012 | Sorting | Verify sorting by Name Z to A | User is successfully logged in and is on the Products page.
TC-013 | TS-013 | Sorting | Verify sorting by Price low to high | User is successfully logged in and is on the Products page.
TC-014 | TS-014 | Sorting | Verify sorting by Price high to low | User is successfully logged in and is on the Products page.
TC-015 | TS-015 | Cart | Verify user can add a product to cart | User is successfully logged in and is on the Products page.
TC-016 | TS-016 | Cart | Verify selected product appears in cart | User is logged in and at least one product has been added to the cart.
TC-017 | TS-017 | Cart | Verify user can remove product from cart | User is logged in and at least one product has been added to the cart.
TC-018 | TS-018 | Cart | Verify cart displays correct product price | User is logged in and at least one product has been added to the cart.
TC-019 | TS-019 | Cart | Verify cart quantity is displayed correctly | User is logged in and at least one product has been added to the cart.
TC-020 | TS-020 | Cart | Verify Continue Shopping functionality | User is logged in and is on the Cart page.
TC-021 | TS-021 | Checkout | Verify user can open checkout | User is logged in and at least one product is present in the cart.
TC-022 | TS-022 | Checkout | Verify checkout form fields are displayed | User is logged in and is on the Checkout Information page.
TC-023 | TS-023 | Checkout | Verify checkout with valid information | User is logged in and is on the Checkout Information page.
TC-024 | TS-024 | Checkout | Verify checkout with empty required fields | User is logged in and is on the Checkout Information page.
TC-025 | TS-025 | Checkout | Verify user can complete an order | User is logged in, at least one product is in the cart, and valid checkout information is available.
TC-026 | TS-026 | Checkout | Verify order confirmation message | User has successfully completed the checkout process and is on the order confirmation page.
TC-027 | TS-027 | Menu | Verify menu can be opened | User is successfully logged in and is on the Products page.
TC-028 | TS-028 | Menu | Verify All Items option | User is logged in and the navigation menu is open.
TC-029 | TS-029 | Menu | Verify About option | User is logged in and the navigation menu is open.
TC-030 | TS-030 | Menu | Verify Reset App State functionality | User is logged in, the navigation menu is open, and at least one product has been added to the cart.

## Exploratory Testing
Exploration ID | Area | Test Data | Observation | Result
ET-001 | Login | locked_out_user / secret_sauce | System displayed "Epic sadface: Sorry, this user has been locked out." and did not allow login. | Expected
ET-002 | Products / Product Image | problem_user / secret_sauce | Some products display an incorrect dog image instead of their corresponding product image. | Defect Found
ET-003 | Product Detail | problem_user / secret_sauce | Bolt T-Shirt product detail page displayed the correct product image, title, description, price, and Add to Cart button. | PASS / No Defect Found
ET-004 | Cart / Remove Product | problem_user / Bolt T-Shirt | Product was successfully removed from the cart after clicking Remove. | Pass
ET-005 | Checkout / Last Name Field | problem_user / secret_sauce | First Name and Postal Code accept input, but the Last Name field does not accept any input. When Continue is clicked, the system displays "Error: Last Name is required." | Defect Found

## Bug Reports
Bug ID | Related Exploration ID | Module | Bug Title | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status
BUG-001 | ET-002 | Products | Incorrect product images displayed for problem_user | Medium | Medium | 1. Open SauceDemo. 2. Login with problem_user / secret_sauce. 3. Navigate to the Products page. 4. Locate the Sauce Labs Backpack product. 5. Observe the product image. | ach product should display its own relevant product image. | Some products, including Sauce Labs Backpack, Sauce Labs Bike Light, and Sauce Labs Bolt T-Shirt, display the same incorrect dog image instead of their respective product images. | Open
BUG-002 | ET-005 | Checkout | Last Name field does not accept input for problem_user | High | High | 1. Open SauceDemo. 2. Login using problem_user / secret_sauce. 3. Add any product to the cart. 4. Open the Cart. 5. Click Checkout. 6. Enter a valid First Name. 7. Try to enter a valid Last Name. 8. Enter a valid Postal Code. 9. Click Continue. | The Last Name field should accept valid text input and the user should be able to continue to the next checkout step. | Tumhare third screenshot ko BUG-002 ka evidence rakhna. It clearly shows the validation error. | Open

## Regression Testing
Regression ID | Test Case ID | Module | Test | Expected Result | Actual Result | Status
RT-001 | TC-001 | Login | Verify login with valid credentials | User should successfully login and reach the Products page. | User successfully logged in and was redirected to the Products page. | PASS
RT-002 | TC-015 | Cart | Verify user can add a product to cart | Selected product should be added to the cart with correct details. | Sauce Labs Backpack was successfully added to the cart with the correct product name, quantity, and price. | PASS
RT-003 | TC-017 | Cart | Verify user can remove a product from cart | Selected product should be removed from the cart. | Sauce Labs Backpack was successfully removed from the cart, the cart became empty, and the cart count was updated. | PASS
RT-004 | TC-023 | Checkout | Verify checkout with valid information | User should proceed successfully to the Checkout Overview page. | User successfully entered valid checkout information and proceeded to the Checkout Overview page. | PASS
RT-005 | TC-025 | Checkout | Verify user can complete an order | Order should be successfully completed and confirmation should be displayed. | Order was successfully completed and the order confirmation message was displayed. | PASS

## Test Plan
SauceDemo Manual Testing - Test Plan
Section | Detials
Project Title | SauceDemo Manual Testing Project
Application Under Test | SauceDemo E-Commerce Web Application
Test Objective | To verify the functionality, usability, validation, navigation, cart, checkout, and menu features of the SauceDemo application through manual testing.
Testing Approach | Manual functional testing, exploratory testing, regression testing, and defect reporting.
Scope | Login, Products, Product Details, Sorting, Cart, Checkout, and Menu functionality.
Out of Scope | Performance testing, security testing, API automation, database testing, and source-code testing.
Testing Types | Functional Testing, UI Testing, Validation Testing, Exploratory Testing, Regression Testing, Retesting.
Test Environment | Google Chrome browser on Windows desktop; SauceDemo web application.
Test Data | Valid and invalid SauceDemo user credentials, product data, cart data, and checkout information.
Test Scenarios | 30
Test Cases | 30
Exploratory Tests | 5
Regression Tests | 5
Defects Identified | 2
Entry Criteria | Application is accessible, test environment is available, test data is prepared, and test cases are documented.
Exit Criteria | All planned test cases are executed, regression testing is completed, identified defects are documented, and test results are summarized.
Deliverables | Test Scenarios, Test Cases, Test Execution Results, Exploratory Testing Records, Bug Reports, Regression Testing Results, and Test Summary Report.
Defect Reporting | Defects are documented with Bug ID, title, severity, priority, steps to reproduce, expected result, actual result, status, and evidence.
Risks & Assumptions | Application behavior may vary by test user. Test results are based on the available SauceDemo environment and browser configuration.
Prepared By | Muhammad Nouman Arshad

## Test Summary Report
Test Summary Report
Section | Details
Project Title | SauceDemo Manual Testing Project
Application Under Test | SauceDemo E-Commerce Web Application
Testing Type | Manual Testing
Test Scenarios | 30
Test Cases Executed | 30
Passed Test Cases | 30
Failed Test Cases | 0
Blocked Test Cases | 0
Pass Rate | 100%
Exploratory Tests Executed | 5
Exploratory Defects Found | 2
Regression Tests Executed | 5
Regression Tests Passed | 5
Regression Tests Failed | 0
Defects Identified | 2
BUG-001 | Incorrect product images displayed for problem_user
BUG-002 | Last Name field does not accept input for problem_user
BUG-002 Retest | Not reproducible with standard_user
Overall Test Result | All planned test cases and regression tests passed successfully. Two defects were identified during exploratory testing and documented with evidence.
Prepared By | Muhammad Nouman Arshad